## service-pack-planning
| Q1 | Q2 | Q3 | Q4
LTSC 1607 |  |  | SP12 | SP13
LTSC 2021 | SP2 | SP3,SP4 | SP5,SP6 | SP7
LTSC 1809 | SP3 |  | SP4 | SP5

## SP Plan - Q1
Product | Scope Finalized | Development | Integration | Verification | Validation | InCenter release
LTSC 1607 | Completed | Completed | In progress | Yet to start | Yet to start | Yet to start
Plan | Wk 20'2026 | Wk 20'2026 | Wk 20'2026 | Wk 20'2026 | Wk 20'2026 | Wk 20'2026
Product | Scope Finalized | Development | Integration | Verification | Validation | InCenter release | Production release
LTSC 1607 SP12 | Completed | Completed | Completed | Completed | Yet to start | Yet to start
Plan | 2025 | 2025 | 2025 | 2025 | Wk 30'2026 | Wk 31'2026
LTSC 2021 SP6 | Completed | In progress | Yet to start | Yet to start | Yet to start | Yet to start
Plan | Wk 27'2026 | Wk 30'2026 | Wk 31'2026
LTSC 1809 SP4 | Completed | Yet to start | Yet to start | Yet to start | Yet to start | Yet to start
Plan | Wk 28'2026 | Wk 32'2026 | Wk 33'2026
LTSC 1607 SP13 | Completed | Yet to start | Yet to start | Yet to start | Yet to start | Yet to start
Plan | Wk 28'2026 | Wk 33'2026 | Wk 34'2026

## SP Plan - Q2
Product | Scope Finalized | Development | Integration | Verification | Validation | InCenter release | Production release
LTSC 2021 SP5 | Completed | In progress | Yet to start | Yet to start | Yet to start | Yet to start
Plan | Wk 27'2026 | Wk 30'2026 | Wk 31'2026
LTSC 2021 SP5 | Completed | In progress | Yet to start | Yet to start | Yet to start | Yet to start
Plan | Wk 27'2026 | Wk 30'2026 | Wk 31'2026
LTSC 2021 SP5 | Completed | In progress | Yet to start | Yet to start | Yet to start | Yet to start
Plan | Wk 27'2026 | Wk 30'2026 | Wk 31'2026

## SP Plan - Q3
Product | Scope Finalized | Development | Integration | Verification | Validation | InCenter release | Production release | Actual
LTSC 2021 SP5 | Completed | Completed | Completed | Completed | Completed | Completed
| WK 24'2026 | WK 27'2026 | WK 27'2026 | WK 29'2026 | WK 29'2026 | Wk 37'2026 |  | Wk 37'2026
LTSC 1809 SP4 | Completed | Completed | In progress | Yet to start | Inprogress | Inprogress
Plan | Wk 28'2026 | Wk 32'2026 | Wk 33'2026 | Wk 35'2026 | Wk 36'2026 | Wk 41'2026 |  | Wk 40'2026
LTSC 1607 SP12 | Completed | Completed | Completed | Completed | Completed | Inprogress
Plan | Wk 28'2026 |  |  |  | Wk 35'2026 | Wk 41'2026 |  | Wk 40'2026

## SP Plan Q4
Product | Scope Finalized | Development | Integration | Verification | Validation | InCenter release | Actual
LTSC 2021 SP6 | Completed | Completed | Yet to start | Yet to start | Yet to start | Yet to start
Plan | Wk 37'2026 | Wk 41'2026 | Wk 42'2026 | WK 44'2026 | WK 46'2026 | WK 47'2026 | WK 47'2026
LTSC 1809 SP5 | Yet to start | Yet to start | Yet to start | Yet to start | Yet to start | Yet to start
Plan | Wk 37'2026 | Wk 44'2026 | Wk 45'2026 | WK 47'2026 | WK 49'2026 | WK 51'2026 | WK 51'2026
LTSC 1607 SP13 | Yet to start | Yet to start | Yet to start | Yet to start | Yet to start | Yet to start
Plan | Wk 37'2026 | Wk 47'2026 | Wk 48'2026 | WK 50'2026 | WK 51'2026 | WK 53'2026 | WK 53'2026